## How to Use
How to use this project schedule template
1. On the Schedule tab, type your project name and start date in the yellow cells at the top.
2. Replace the example activities with your own. Give each one a short ID (A, B, C... or 1, 2, 3...).
3. Enter a duration in working days. Use 0 for milestones such as sign-offs or go-live.
4. Enter up to two predecessors by ID. The activity starts on the next working day after its latest predecessor finishes.
5. Add holidays and shutdown days on the Holidays tab. Dates recalculate automatically.
6. Track progress with % Complete and Status. Keep a copy of the first approved version as your baseline.
Tips
- Break work down until each activity takes no more than about two weeks.
- Put approvals, reviews and supplier lead times in as real activities. They are the usual reason schedules slip.
- The critical path is the longest chain of dependent activities. A delay on it moves the finish date.
- More on building and managing schedules: https://mymanagementguide.com/basics/project-schedule/

## Schedule
Project Schedule Template
MyManagementGuide.com ¦ Edit the yellow cells and blue text. Dates, Gantt bars and totals update automatically.
|  | Project name | Company website redesign (example) |  |  |  | Legend: | Input | Task bar | Milestone
|  | Project start date | 2027-01-04 |  |  |  | Durations are in working days (Mon-Fri, minus dates on the Holidays tab). Duration 0 = milestone.
|  | Project finish | 2027-03-02 |  |  |  | Up to two predecessors per activity (finish-to-start). Leave blank if the activity can start on the project start date.
|  | Total duration (working days) | 42
Gantt chart: one column per week (week starting Monday)
ID | WBS | Activity | Owner | Duration (days) | Predecessor 1 | Predecessor 2 | Start | Finish | % Complete | Status | Next free day | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28
A | 1.1 | Kickoff and requirements | Project manager | 5 |  |  | 2027-01-04 | 2027-01-08 | 100% | Done | 2027-01-11
B | 1.2 | Sitemap and content plan | UX lead | 5 | A |  | 2027-01-11 | 2027-01-15 | 100% | Done | 2027-01-18
C | 2.1 | Visual design | Designer | 10 | B |  | 2027-01-18 | 2027-01-29 | 50% | In progress | 2027-02-01
D | 2.2 | Content writing | Content writer | 15 | B |  | 2027-01-18 | 2027-02-05 | 30% | In progress | 2027-02-08
E | 3.1 | Front-end development | Front-end developer | 15 | C |  | 2027-02-01 | 2027-02-19 | 0% | Not started | 2027-02-22
F | 3.2 | CMS setup and back end | Back-end developer | 8 | C |  | 2027-02-01 | 2027-02-10 | 0% | Not started | 2027-02-11
G | 3.3 | Load content into CMS | Content writer | 5 | D | F | 2027-02-11 | 2027-02-17 | 0% | Not started | 2027-02-18
H | 4.1 | Testing and fixes | QA lead | 5 | E | G | 2027-02-22 | 2027-02-26 | 0% | Not started | 2027-03-01
I | 4.2 | Client sign-off (milestone) | Sponsor | 0 | H |  | 2027-03-01 | 2027-03-01 | 0% | Not started | 2027-03-01
J | 4.3 | Launch and handover | Project manager | 2 | I |  | 2027-03-01 | 2027-03-02 | 0% | Not started | 2027-03-03
Example rows show a 42-working-day website redesign with a critical path of A-B-C-E-H-I-J. Replace them with your own activities. Source: worked example from MyManagementGuide's project schedule guide.
Formulas:
Company website redesign (example) = NETWORKDAYS(D5,[Company website redesign (example), row above],Holidays!$A2:A40)
Legend: = IF([Project name]="","",WORKDAY(WORKDAY(MAX(D5,IF(F11="",D5,IFERROR(INDEX(L11:L60,MATCH(F11,A11:A60,0)),D5)),IF(G11="",D5,IFERROR(INDEX(L11:L60,MATCH(G11,A11:A60,0)),D5))),-1,Holidays!$A2:A40),1,Holidays!$A2:A40))
Input = IF([Project name]="","",IF(E11=0,[Legend:],WORKDAY([Legend:],E11-1,Holidays!$A2:A40)))

## Holidays
Non-working dates | Name
| Add dates in column A, e.g. Jan 18, 2027 (company holiday) | List public holidays and shutdown days here. Start and finish dates skip them automatically.